## Autodeadline table
Scientific Editing and Research Communication Core (SERCC) Recommended Timeline for NIH Fellowships
| Type in Sponsor's Deadline (SD) –> | 2025-12-08
3 months before SD | Contact your departmental administrator to coordinate with the Division of Sponsored Programs (DSP) for Cayuse access and eRA Commons ID | 2025-09-01
Read Notice of Funding Opportunity (NOFO) and check Notice of Special Interest (NOSI) to see if any are relevant to you.
| Begin drafting the Training Activities & Timeline (3 pages) | 2025-09-08
| Begin drafting the Research Training Project: Specific Aims (1 page) and Research Strategy (6 pages) | 2025-09-15
| Begin seeking IRB or IACUC approvable (if applicable). | 2025-09-22
Contact NIH Program Officer(s). Send them the current draft of your Specific Aims page for reference.
Write your Biosketch (5 pages)
Solicit mentors' Biosketches (5 pages)
| Begin drafting Goals, Preparedness, and Potential (3 pages) | 2025-09-29
2 months before SD | Write Facilities & Other Resources (no page limit) | 2025-10-06
| Write Training in Responsible Conduct of Research (1 page) | 2025-10-13
Write Equipment (no page limit)
| Solicit Letters of Support from Collaborators, Contributors, and Consultants (6 pages total) | 2025-10-20
| Solicit Letters of Reference | 2025-10-27
Solicit Sponsor(s) Commitment (6 pages). Send mentor(s) your Biosketch, Facilities & Other Resources, and Applicant's Background & Goals for Fellowship Training for reference.
1 month before SD | Complete Human Subjects/Vertebrate Animals (as applicable) | 2025-11-03
| Write Project Summary/Abstract (30 lines of text) | 2025-11-10
Write Project Narrative (3 sentences)
| Complete Budget | 2025-11-17
Write Cover Letter
Finalize entire grant for departmental administrator to review and submit to DSP. Follow up with referees.
5 business days before SD | ENTIRE GRANT DUE TO DSP | 2025-12-01
SD | ENTIRE GRANT DUE TO SPONSOR | 2025-12-08
The University of Iowa ¦ Roy J and Lucille A Carver College of Medicine ¦ COM-ScientificEditing@uiowa.edu ¦ https://medicine.uiowa.edu/editingcore
Blue text indicates sections of the application completed by the trainee
Red text indicates sections of the application completed by other team members